## Home
Project Name | ICTAK Trainer Management System | https://trainermanagement.herokuapp.com/
Module Name | Home
Created By | Swathy Sagar
Created Date | 2022-11-25
Reviewed By | Test Manager
Reviewed Date
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_HE_02 | DEF_TMS_HE_01 | Social media links should be working properly. | Social media links are not working | 1) Open the site https://trainermanagement.herokuapp.com/ 2 ) Click on social media links | Minor | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_HE_04 | DEF_TMS_HE_02 | Contact details, support details, Head office details and Copyright should be given on the home page. | Contact details, support details, Head office details and Copyright are not given on the home page | 1) Open the site https://trainermanagement.herokuapp.com/ 2) scroll down the page | Minor | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_HE_06 | DEF_TMS_HE_03 | Images should be display correctly | The course details displayed without alignment in Firefox browser | 1) Try to open the website in different browsers | Minor | Medium | New

## Login
Project Name | ICTAK Trainer Management System | https://trainermanagement.herokuapp.com/
Module Name | Login
Created By | Swathy Sagar
Created Date | 2022-11-25
Reviewed By | Test Manager
Reviewed Date
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_LN_06 | DEF_TMS_LN_01 | Should be able to reset the password from login page | unable to reset the password from login page | 1) Open the site https://trainermanagement.herokuapp.com/login 2) Try to reset the password | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_LN_09 | DEF_TMS_LN_02 | Social media links should be working properly. | Social media links are not working | 1) Open the site https://trainermanagement.herokuapp.com/login 2) Click on facebook,Instagram,Twitter icon | Minor | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_LN_11 | DEF_TMS_LN_03 | Should not take too much time to load the home page after login | It take more time to load home page | 1) Open the site https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) Click on Sign in button | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_LN_13 | DEF_TMS_LN_04 | Should not take the use to log out mode | When click on browser back button it take the user to log out mode | 1) Open the site https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) Click on Sign in button 4) Click on browser back button | Major | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_LN_18 | DEF_TMS_LN_05 | Password should not be copy pasted | The password can be copy pasted | 1) Open the site https://trainermanagement.herokuapp.com/login 2) Enter email id and try to copy paste the password 3) Press 'enter' key | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_LN_20 | DEF_TMS_LN_06 | Closing the browser should not log-out an authenticated user | When closing the browser, it log-out an authenticated user | 1) Open the site https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) Press 'enter' key 4) close the website | Minor | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_LN_21 | DEF_TMS_LN_07 | There should be a limit on the total number of unsuccessful login attempts | No limit is defined on the total number of unsuccessful login attempts | 1) Open the site https://trainermanagement.herokuapp.com/login 2) Try to login 5 times with incorrect password/ email id | Minor | Medium | New

## Sign up
Project Name | ICTAK Trainer Management System | https://trainermanagement.herokuapp.com/
Module Name | Sign Up
Created By | Swathy Sagar
Created Date | 2022-11-25
Reviewed By | Test Manager
Reviewed Date
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_SU_01 | DEF_TMS_SU_01 | Social media links should be working properly. | Social media links are not working | 1) Open the website 2) Click on "sign up" 3) Try to click on social media links | Minor | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_SU_03 | DEF_TMS_SU_02 | Should not accept invalid email id. | Email' field accepted some invalid email id and not accepted some valid email id. | 1) Open the website 2) Click on "sign up" 3) Click on Email field 4) Try to enter valid and invalid email id | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_SU_04 | DEF_TMS_SU_03 | Mobile number should be validated | It accepted some invalid mobile number | 1) Open the website 2) Click on "sign up" 3) Click on Mobile No field 4) Try to enter mobile numbers | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_SU_08 | DEF_TMS_SU_04 | Should not allow duplicate entry | Allowed duplicate entry and able to view in admin approval age. | 1) Open the website 2) Click on "sign up" 3) Try to sign up with duplicate data | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_SU_14 | DEF_TMS_SU_05 | Should not allow already existing email id | It accepted already existing email id | 1) Open the website 2) Click on "sign up" 3) Try to sign up with already existing email id | Minor | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_SU_17 | DEF_TMS_SU_06 | Password should not be copy pasted | The password can be copy pasted | 1) Open the website 2) Click on "sign up" 3) Try to copy paste password and Re-type password | Minor | Medium | New

## Admin Approval
Project Name | ICTAK Trainer Management System | https://trainermanagement.herokuapp.com/
Module Name | Admin Approval
Created By | Swathy Sagar
Created Date | 2022-11-25
Reviewed By | Test Manager
Reviewed Date
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_AA_01 | DEF_TMS_AA_01 | Social media links should be working properly. | Social media links are not working | 1) Open the website 2) Login to the website as admin 3) Try to click on social media links | Minor | Medium | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_AA_06 | DEF_TMS_AA_02 | A placeholder should be there for employment type drop down | The placeholder is not available | 1) Open the website 2) Login to the website as admin 3) Try find the placeholder on employment type drop down | Trivial | Low | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_AA_07 | DEF_TMS_AA_03 | Should not approve the trainer without specifying the employment type | Able to approve the trainer without specifying the employment type | 1) Open the website 2) Login to the website as admin 3) Try to click on approve button without specifying employment type | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_AA_12 | DEF_TMS_AA_04 | Should not approve duplicate entries in trainer details | Able to approve duplicate entries in trainer details | 1) Open the website 2) Login to the website as admin 3) Approve the duplicate entries in trainer details | Major | High | New
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_AA_13 | DEF_TMS_AA_05 | Should not allow multiple clicks on 'Approve' button | Able to click multiple times on 'Approve' button and trainer get multiple emails from admin side | 1) Open the website 2) Login to the website as admin 3) Click multiple times on 'Approve' button | Major | High | New

## Allocate_Trainer
Project Name | Trainer Management System | https://trainermanagement.herokuapp.com/
Module Name | Allocate and trainer allocate page
Created By | Sneha N
Created Date | 2022-09-23
Reviewed by | Test Manager
Reviewed date | 2022-11-26
TESTCASE ID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_ALC_05 | DEF_TMS_TA_01 | option for type of trainer should be their in allocate page. | such an option is not provided | 1) Open the site https://trainermanagement.herokuapp.com/admin 2) Enter email id and password 3) click on Sigin In button and go to allocate page 4) type Type of trainer on serach button | Major | High | New
TESTCASE ID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_ALC_12 | DEF_TMS_TA_02 | time delay should not be their for loading the page back to allocate page from trainer allocate page | taking time to load back to allocate page from allocate trainer page | 1) Open the site https://trainermanagement.herokuapp.com/admin 2) Enter email id and password 3) click on Sigin In button and go to allocate page 4)Click on allocate button 5)Click back option | Medium | Low | New
TESTCASE ID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_ALC_13 | DEF_TMS_TA_03 | allocate trainer page should appear in top to bottom | In some entries its showing in bottom to top format and we need to scroll up to view the title and other details in allocate trainer page | 1) Open the site https://trainermanagement.herokuapp.com/admin 2) Enter email id and password 3) click on Sigin In button and go to allocate page 4)Click on allocate button | Low | Low | New
TESTCASE ID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_31 | DEF_TMS_TA_04 | Time-00:00 should not be able to allocate | time 00:00 should be considered as invalid and warning message should come | 1)Click on allocate button in allocate page 2)enter the time and other details 3)click on allocate button in trainer allocate page | Major | High | New
TESTCASE ID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_36 | DEF_TMS_TA_05 | date format in trainer allocate page should be as same as the format of date in received mail | start date-24/11/2022 , End date-12/05/2022:-in allocate trainer page ;start date-2022-11-24 , End date-2022-05-12 both are indifferent format | 1)Click on allocate button in allocate page 2)enter the Start date,End date 3)click on allocate button in trainer allocate page | Low | low | New
TESTCASE ID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_38 | DEF_TMS_TA_06 | If same dates for same trainer is given calender should be blocked | same trainer with the same dates can be entered twice and redundant datas are viewed in view allocation page | 1)Click on allocate button in allocate page 2)enter the Start date,End date 3)click on allocate button in trainer allocate page | Critical | High | New
TESTCASE ID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_39 | DEF_TMS_VA_07 | invalid link format and numbers wont be accepted | invalid link format and numbers is accepted | 1)Click on allocate button in allocate page 2)enter the Start date,End date 3)click on allocate button in trainer allocate page | Critical | High | New

## View Allocation
Project Name | Trainer Management System | https://trainermanagement.herokuapp.com/
Module Name | View Allocation
Created By | Sruthi Ashish
Created Date | 2022-11-25
Reviewed by
Reviewed date
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_05 | DEF_TMS_VA_01 | When we type CourseID:CSA in search bar the result should display the details of all trainers allocated to particular course only | Displaying details of trainers allocated to all courses | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type CourseID asCSA 5)Check whether details of all trainers allocated to the particular course are displaying correctly based on the course ID's given | Low | Low | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_06 | DEF_TMS_VA_02 | When we type CourseID:DSA in search bar the result should display the details of all trainers allocated to particular course only | Displaying details of trainers allocated to all courses | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type CourseID as DSA 5)Check whether details of all trainers allocated to the particular course are displaying correctly based on the course ID's given | Low | Low | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_07 | DEF_TMS_VA_03 | When we type CourseID :RPA in search bar the result should display the details of all trainers allocated to particular course only | Displaying details of trainers allocated to all courses | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type CourseID as RPA 5)Check whether details of all trainers allocated to the particular course are displaying correctly based on the course ID's given | Low | Low | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_08 | DEF_TMS_VA_04 | When we type CourseID :FSD in search bar the result should display the details of all trainers allocated to particular course only | Displaying details of trainers allocated to all courses | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type CourseID as FSD 5)Check whether details of all trainers allocated to the particular course are displaying correctly based on the course ID's given | Low | Low | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_17 | DEF_TMS_VA_05 | When we type name in search bar, the result shouldn’t display any duplicate records | Duplicate record exist for name with same ID | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type name | Major | medium | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_18 | DEF_TMS_VA_06 | When we type time in search bar result should display records of trainer allocated to that particular time | Displaying details of trainers whose scheduled time is different to that of given in the search filter | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type time 5)Check whether details of all trainers allocated to the particular time are displaying correctly | low | low | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_19 | DEF_TMS_VA_07 | When we type invalid time in search bar result shouldn't display any records | Records with invalid time exists | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type time as 00:00 5)Check whether any record is displaying | medium | medium | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_20 | DEF_TMS_VA_08 | When we type invalid date in search bar result shouldn't display any records | Records with invalid date exists | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type Invalid date as :0022-02-28 5)Check whether any record is displaying | medium | medium | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_21 | DEF_TMS_VA_09 | When we type valid date in search bar result should display records allocated for that particular date | Record exists but its not displaying while giving search filter | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type valid date as 2022-01-13 5)Check whether any record is displaying | medium | medium | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_23 | DEF_TMS_VA_10 | When we type valid date in search bar result should display records allocated for that particular date only | Displaying records other than the trainers allocated to the date given in search bar. | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type valid date 5)Check whether all trainers allocated for particular enddate are displaying correctly | medium | medium | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_25 | DEF_TMS_VA_11 | When we search meeting link, it should be valid | Displaying links which are not valid | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)View the results displayed | major | high | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_26 | DEF_TMS_VA_12 | When we search meeting link, it shouldn’t be text,number or anything other than hyperlink | Displaying links which are not hyperlinks. Displaying invalid links like text and number | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link. 3)Click on Search option. 4) Type any text or number 5)Check whether all details are displaying correctly based on the link given | major | high | New
TESTCASEID | BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | STATUS
TMS_TC_31 | DEF_TMS_VA_13 | When we click View allocation link multiple times the allocated details should be displayed without any delay | Details are displaying only after a short delay | 1) Open the application https://trainermanagement.herokuapp.com/admin/viewallocationProject. 2)Click on ViewAllocation Link multiple times | medium | medium | New

## TMS Edit Profile - Bug Report
Project Name |  | TRAINER MANAGEMENT SYSTEM | https://trainermanagement.herokuapp.com/
Module Name |  | Edit Profile
Created By |  | Sasilekha Siloshe T
Created Date |  | 2022-11-25
Reviewed By |  | Test Manager
Reviewed Date
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_01 | Edit_profile_33 | Should not allow the user to enter whitespace as a valid name. | Whitespace validation not implemented. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Name text field 7) Enter whitespaces as name. 8) Enter other fields as well 9) Click Edit button 10) Go to Profile page and verify the trainer name | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_02 | Edit_profile_34 | Should not allow the user to enter whitespace as a valid address. | Whitespace validation not implemented. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on address text field 7) Enter whitespaces as address. 8) Enter other fields as well 9) Click Edit button 10) Go to Profile page and verify the trainer address. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_03 | Edit_profile_35 | Should not allow the user to enter whitespace as a valid qualification. | Whitespace validation not implemented. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Highest Qualification text field 7) Enter whitespaces as qualification 8) Enter other fields as well 9) Click Edit button 10) Go to Profile page and verify the trainer qualification. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_04 | Edit_profile_36 | Should not allow the user to enter whitespace as a valid skill. | Whitespace validation not implemented. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Skill Set text field 7) Enter whitespaces as skill 8) Enter other fields as well 9) Click Edit button 10) Go to Profile page and verify the trainer skill set. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_05 | Edit_profile_37 | Should not allow the user to enter whitespace as a valid company. | Whitespace validation not implemented. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Current Company Name text field 7) Enter whitespaces as company name 8) Enter other fields as well 9) Click Edit button 10) Go to Profile page and verify the trainer company name. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_06 | Edit_profile_38 | Should not allow the user to enter whitespace as a valid designation. | Whitespace validation not implemented. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Current Designation text field 7) Enter whitespaces as designation. 8) Enter other fields as well 9) Click Edit button 10) Go to Profile page and verify the trainer designation. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_07 | Edit_profile_39 | Allow the user to enter name character count greater than 25 s well. | The name like mohandas karamchand gandhi is not allowing to save.It is good to have to allow at least 50 character ccount in name text field. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Name text field 7) Enter mohandas karamchand gandhie as name 8) "Enter valid name" error will prompt. | Medium | Low | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_08 | Edit_profile_40 | Allow the user to enter email id with underscore character. | Email id with underscore is a valid email. So it should be allowed. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Email text field 7) Enter abc_def@gm.com as email. 8) "Enter valid email id" error will prompt. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_09 | Edit_profile_41 | Should not allow the user to enter whitespace as a valid mobile number. | Whitespace validation not implemeted for mobile number. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Mobile No. text field 7) Enter 10 whitespace as mobile number. 8) Click Edit button. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_10 | Edit_profile_42 | The # character should be allowed to represent a house number in address. | The # character is commonly used in address to specify house number or building number. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Address text field 7) Enter Home #1234 as address. 8) "Enter valid address" error will prompt. | Medium | Low | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_11 | Edit_profile_43 | Should allow the user to enter course title along with or without course abbrevation. | Due to maximum 25 number of character validation some of the course title are not allowed to save. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Highest Qualification text field 7) Enter bachelor of computer application as qulification. 8) "Enter valid qualification" error will prompt. | Medium | Low | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_12 | Edit_profile_44 | Should allow the user to enter skills which have only one character to represent it. | Due to minimum 2 number of character validation some of the skills are not allowed to save. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Skill Set text field 7) Enter C as skill 8) "Enter valid skills" error will prompt. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_13 | Edit_profile_45 | Should allow the user to enter skills which have special character along with it. | Due to skill set text field only accepting alphanumeric data, some of the skills with special characters are not allowing to save. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Skill Set text field 7) Enter C# as skill 8) "Enter valid skills" error will prompt. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_14 | Edit_profile_46 | Should allow the user to enter company name which have numbers along with it. | Due to Current Company text field only accepting alphabets, company names wth numbers are not allowing. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Current Company text field 7) Enter Viacom 18 as company name 8) "Enter valid company name" error will prompt. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
DP_Bug_15 | Edit_profile_47 | Should allow the user to enter company name which have symbols along with it. | Due to Current Company text field only accepting alphabets, company names with symbols are not allowing. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Current Company text field 7) Enter AT & T as company name 8) "Enter valid company name" error will prompt. | Major | High | New
Bug Id | Test Case Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
EDP_Bug_16 | Edit_profile_48 | Should allow the user to enter company name which have characters more than 25 as well. | Due to Current Company text field only accepting alphabets maximum of 25 characters some of the company names are not allowed. | 1) Login to TMS using Trainer credential https://trainermanagement.herokuapp.com/login 2) Enter email id and password 3) click on Sigin In button 4) Profile page will be rendered 5) Click Edit Profile button 6) Click on Current Company text field 7) Enter Infospica Consultancy Services LLP as company name 8) "Enter valid company name" error will prompt. | Medium | Low | New

## My Allocation&logout
Project Name | ICTAK Trainer Management System | https://trainermanagement.herokuapp.com/
Module Name | My allocation details and logout
Created By | Vidya M Mathew
Created Date | 2022-11-25
Reviewed By | Test Manager
Reviewed Date | 2022-11-26
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_Myalloc_02 | DEF_TMS_MA_01 | the same course should not be allocated twice to the same trainer. | The same course is getting allocated more than once to the trainer of a batch. | 1)Open site(https://trainermanagement.herokuapp.com/). 2) Click on login link. 3)Enter the registered mail id and password. 4)Go to my allocation details page. 5) Check if same course is allocated more than once | medium | medium | new
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_Myalloc_03 | DEF_TMS_MA_02 | If trainer is same, different start and end dates should be allocated for different courses to reduce work load. | The start and end dates allocated to the same trainer for different courses are the same | 1)Open site(https://trainermanagement.herokuapp.com/). 2) Click on login button. Enter the registered mail id and password. 3)Click on My allocation details link. 4) Check if the dates are getting clashed or not | major | medium | new
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_Myalloc_04 | DEF_TMS_MA_03 | If the trainer is same, the time slots allocated for different courses should not get clashed. | The time slots allocated for different courses are getting clashed as a trainer can handle only one subject at a time. | 1) Open site 2) Click on login button 3) Enter the registered mail id and sign in as trainer. 4) Go to trainer profile details 5) Check if time slots are getting clashed or not. | major | major | new
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_Myalloc_05 | Def_TMS_MA_04 | Course id for different subjects should be different and batch id should be unique for different batches. | Course id is given as same for two different subjects. Batch id is also repeated for different batches. | 1) Open site 2) Click on login button 3) Enter the registered mail id and sign in as trainer. 4) Go to course allocation details page 5) Check the course id and batch id for different courses are getting repeated or not | medium | medium | new
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_logout_03 | DEF_TMS_MA_05 | After clicking logout button without internet connection and when we try to login again, should show a warning that not properly logged out. | We click the logout button without internet connection. Later on,error message ‘not properly logged out’ is not showing when we try to login again | 1)Go to the site (https://trainermanagement.herokuapp.com/) 2) Sign in with registered mail id and password. 3)Enter homepage and click logout button without internet connection. | low | low | new
Test Case id | Bug Id | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Status
TMS_Myalloc_06 | DEF_TMS_MA_06 | In The My allocation details page , the venue meeeting link should be clickable | the meeting link is not clickable | 1) Open site 2) Click on login button 3) Enter the registered mail id and sign in as trainer. 4) Go to trainer profile details 5)Check if the venue link given is clickable or not. | medium | medium | new