## TEST EXECUTION REPORT
TEST EXECUTION REPORT
Module | Scenarios | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Admin | Enter both valid and invalid login details for admin and check that the home page is displayed or not. | Medium | Swathy Sagar | 2022-11-25 | Pass
| Verify that Admin Approval is working or not | Medium | Swathy Sagar | 2022-11-25 | Fail | DEF_TMS_AA_03:-Able to approve the trainer without specifying the employment type DEF_TMS_AA_04:- Able to approve duplicate entries in trainer details DEF_TMS_AA_05:-Able to click multiple times on 'Approve' button and trainer get multiple emails from admin side | Major | New
Trainer | Enter both valid and invalid login details for Trainer and check that the home page is displayed or not. | Medium | Swathy Sagar | 2022-11-25 | Pass
| Enter both valid and invalid Sign up details for Trainer and check that it comes in the Admin home page. | Medium | Swathy Sagar | 2022-12-25 | Fail | DEF_TMS_SU_02 :- 'Email' field accepted some invalid email id and not accepted some valid email id. DEF_TMS_SU_03:-It accepted some invalid mobile number. | Major | New
| Verify Social media links | Medium | Swathy Sagar | 2022-12-25 | Fail | DEF_TMS_SU_01:-Social media links are not working | Minor | New
| Verify that duplicate entry from Sign up page is allowed or not | Medium | Swathy Sagar | 2022-12-25 | Fail | DEF_TMS_SU_04:-Allowed duplicate entry and able to view in admin approval age. | Major | New
Admin | Examine the search functions | Medium | Sneha N | 2022-11-25 | 4 test cases pass ,1 test case fail | DEF_TMS_TA_01 -option for type of trainer is not their in allocate page. | Major | New
| Check the allocate page contents | Medium | Sneha N | 2022-11-25 | Pass
| Check the allocate button and allocate trainer functionality | Medium | Sneha N | 2022-11-25 | 6 test cases fail, 28 test cases pass | DEF_TMS_TA_02 - taking time to load back to allocate page from allocate trainer page DEF_TMS_TA_03- In some entries its showing in bottom to top format and we need to scroll up to view the title and other details in allocate trainer page. DEF_TMS_TA_04 -time 00:00 should be considered as invalid and warning message should come. DEF_TMS_TA_05- start date-24/11/2022 , End date-12/05/2022:-in allocate trainer page ;start date-2022-11-24 , End date-2022-05-12 both are indifferent format DEF_TMS_TA_06 DEF_TMS_TA_07invalid link format and numbers is accepted | DEF_TMS_TA_02 Medium DEF_TMS_TA_03Low DEF_TMS_TA_04Major DEF_TMS_TA_05Low DEF_TMS_TA_016Critical DEF_TMS_TA_07Critical | New
Admin | Verify the displayed data in View allocation is correct or not | Medium | Sruthi Ashish | 2022-11-25 | Pass
| Verify the search functionality of View allocation page | Medium | Sruthi Ashish | 2022-11-25 | 12 Test cases Failed 16 Test Cases Passed | DEF_TMS_VA_01, DEF_TMS_VA_02, DEF_TMS_VA_03, DEF_TMS_VA_04(Displaying details of trainers allocated to all courses) DEF_TMS_VA_05(Duplicate record exist for name with same ID) DEF_TMS_VA_06(Displaying details of trainers whose scheduled time is different to that of given in the search filter) DEF_TMS_VA_07 (Records with invalid time exists) DEF_TMS_VA_08(Records with invalid date exists) DEF_TMS_VA_09 (Record exists but its not displaying while giving search filter) DEF_TMS_VA_10(Displaying records other than the trainers allocated to the date given in search bar.) DEF_TMS_VA_11(Displaying links which are not valid) DEF_TMS_VA_12(Displaying links which are not hyperlinks. Displaying invalid links like text and number) | DEF_TMS_VA_01 Low DEF_TMS_VA_02 Low DEF_TMS_VA_03 Low DEF_TMS_VA_04 Low DEF_TMS_VA_05 Major DEF_TMS_VA_06 low DEF_TMS_VA_07 medium DEF_TMS_VA_08 medium DEF_TMS_VA_09 medium DEF_TMS_VA_10 medium DEF_TMS_VA_11 major DEF_TMS_VA_12 major | New
| Verifying other links on the view allocation page | Medium | Sruthi Ashish | 2022-11-25 | TMS_TC_33 Failed other test cases Passed | DEF_TMS_VA_13(When we click View allocation link multiple times the allocated details should be displayed without any delay) | Medium | New
| Verify the logout functionality | High | Sruthi Ashish | 2022-11-25 | Pass
| Verifying other links on the view allocation page | Medium | Sruthi Ashish | 2022-11-25 | TMS_TC_33 Failed other test cases Passed | DEF_TMS_VA_13(When we click View allocation link multiple times the allocated details should be displayed without any delay) | Medium | New
| Verify the logout functionality | High | Sruthi Ashish | 2022-11-25 | Pass
Trainer Profile | Verify the edit profile functionalityof a trainer | Medium | Sasilekha Siloshe T | 2022-11-25 | 32 Test Cases Passed 16 Test cases Failed | DEF_EDP_Bug_01 - Whitespace validation not implemented. | Major | New
[6 empty] | DEF_EDP_Bug_02 - Whitespace validation not implemented. | Major
[6 empty] | DEF_EDP_Bug_03 - Whitespace validation not implemented. | Major
[6 empty] | DEF_EDP_Bug_04 -Whitespace validation not implemented. | Major
[6 empty] | DEF_EDP_Bug_05 - Whitespace validation not implemented. | Major
[6 empty] | DEF_EDP_Bug_06 - Whitespace validation not implemented. | Major
[6 empty] | DEF_EDP_Bug_07 - The name like mohandas karamchand gandhi is not allowing to save.It is good to have to allow at least 50 character ccount in name text field. | Medium
[6 empty] | DEF_EDP_Bug_08 - Email id with underscore is a valid email. So it should be allowed. | Major
[6 empty] | DEF_EDP_Bug_09 - Whitespace validation not implemeted for mobile number. | Major
[6 empty] | DEF_EDP_Bug_10 - The # character is commonly used in address to specify house number or building number | Medium
[6 empty] | DEF_EDP_Bug_11 - Due to maximum 25 number of character validation some of the course title are not allowed to save. | Medium
[6 empty] | DEF_EDP_Bug_12 - Due to minimum 2 number of character validation some of the skills are not allowed to save. | Major
[6 empty] | DEF_EDP_Bug_13 - Due to skill set text field only accepting alphanumeric data, some of the skills with special characters are not allowing to save. | Major
[6 empty] | DEF_EDP_Bug_14 - Due to Current Company text field only accepting alphabets, company names wth numbers are not allowing. | Major
[6 empty] | DEF_EDP_Bug_15 - Due to Current Company text field only accepting alphabets, company names with symbols are not allowing. | Major
[6 empty] | DEF_EDP_Bug_16 - Due to Current Company text field only accepting alphabets maximum of 25 characters some of the company names are not allowed. | Medium
Trainer | Go to my allocation details tab and check if course information details of trainer is visible or not and if everything is in right format. | Low | Vidya M Mathew | 2022-12-25 | fail | DEF_TMS_Myalloc_02 - same course is allocated twice to the same trainer. DEF_TMS_Myalloc_03 - same start and end dates are allocated for different courses to same trainer DEF_TMS_Myalloc_04 - time slots allocated are getting clashed DEF_TMS_Myalloc_05 - Course and batch id are getting repeated. DEF_TMS_Myalloc_06 - The venue meeting link is not clickable | DEF_TMS_Myalloc_02 -Low DEF_TMS_Myalloc_03-Low DEF_TMS_Myalloc_04 -Medium DEF_TMS_Myalloc_05 -Medium DEF_TMS_Myalloc_06 -Medium | New
Trainer | Verify whether the logout functionality is working fine or not. | Low | Vidya M Mathew | 2022-12-25 | fail | DEF_TMS_logout_03 – Not showing any warning sign for improper logout | DEF_TMS_logout_03 –Medium | New