## TEST AUTOMATIONEXECUTION REPORT
TEST AUTOMATION EXECUTION REPORT
Module | Scenarios | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Admin | Enter both valid and invalid login details for admin and check that the home page is displayed or not. | Medium | Swathy Sagar | 2022-11-30 | Pass
Trainer | Enter both valid and invalid login details for Trainer and check that the home page is displayed or not. | Medium | Swathy Sagar | 2022-11-30 | Pass
| Enter both valid and invalid Sign up details for Trainer and check that it comes in the Admin home page. | Medium | Swathy Sagar | 2022-12-02 | Not executed ( Because of Application Error in the Website ICTAK Trainer Management System)
Admin | Check whether admin is able to login to system with valid login details | Medium | Sruthi Ashish | 2022-11-27 | Pass
| Check whether admin is able to approve trainer by selecting employement type from dropdown in the admin appproval page. | Medium | Sruthi Ashish | 2022-11-28 | Pass
| Check whether alocation page is able to automate | Medium | Sruthi Ashish | 2022-11-29 | Pass
| Check whether admin is able to allocate trainer by giving valid and invalid test data | Medium | Sruthi Ashish | 2022-11-30 | Pass
| verify whether search functionality of allocation page is working with valid test data | Medium | Sruthi Ashish | 2022-11-01 | Pass
| verify whether search functionality of allocation page is working with invalid test data | Medium | Sruthi Ashish | 2022-12-02 | Not executed ( Because of Application Error in the Website ICTAK Trainer Management System)
| Check whether admin is able to login to system with invalid login details | Medium | Sruthi Ashish | 2022-12-02 | Not executed ( Because of Application Error in the Website ICTAK Trainer Management System)
Admin | Check whether admin is able to login to system with valid login details | Medium | Sneha N | 2022-11-30 | Pass
| Verify the search option in view allocation page by passing valid data | Medium | Sneha N | 2022-11-30 | Pass
| Verify the View allocation page is working or not | Medium | Sneha N | 2022-12-01 | Pass
| Verify logout functionality | Medium | Sneha N | 2022-12-01 | Pass
| Check whether admin is able to login to system with invalid login details | Medium | Sneha N | 2022-12-02 | Not executed ( Because of Application Error in the Website ICTAK Trainer Management System)
| verify whether search functionality of View allocation page is working with invalid test data | Medium | Sneha N | 2022-12-02 | Not executed ( Because of Application Error in the Website ICTAK Trainer Management System)
Trainer | Verify whether the Trainer Profile Displayed correctly. | Medium | Sasilekha Siloshe T | 2022-11-30 | Pass
| Verify whether the Trainer Edit Profile functionality working correctly. | Medium | Sasilekha Siloshe T | 2022-11-30 | Some test cases are executed. Could not execute the whole test cases due to unavailability of the Website www.trainer managent.herocuapp.com.
Trainer | Enter the registered mail id and password of trainer and check if its navigated to the homepage. | Medium | Vidya M Mathew | 11/29/2022 | Pass
| Click on My allocation details tab and check if it takes you to the course information details page of trainer. | Medium | Vidya M Mathew | 11/30/2022 | Pass
| Click on logout button and check if it logs out of the homepage | Low | Vidya M Mathew | 2022-02-12 | Not executed ( Because of Application Error in the Website ICTAK Trainer Management System)