## Jira_Excel_Group 4
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Watchers | Watchers Id | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Sprint | Status Category
Performance Testing- ICTAK website | TMS-60 | 10066 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Vidya M Mathew | 635a8b03928dc277b905384f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-09 19:54 | 2022-12-10 20:20 | 2022-12-10 20:39 | 2022-12-10 20:20 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 4 | Done
Performance Testing- ICTAK website | TMS-59 | 10065 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sruthi Ashish | 635a943ac97f5473af707eb5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-09 19:53 | 2022-12-10 17:01 | 2022-12-10 20:40 | 2022-12-10 17:01 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 4 | Done
Performance Testing- ICTAK website | TMS-58 | 10064 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sneha N | 63811a65f6c85b343c093de5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-09 19:53 | 2022-12-10 20:19 | 2022-12-10 20:40 | 2022-12-10 20:19 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 4 | Done
Performance Testing- ICTAK website | TMS-57 | 10063 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | SASILEKHA SILOSHA | 635a7df101c2ff842c18769b | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-09 19:53 | 2022-12-10 17:22 | 2022-12-10 20:40 | 2022-12-10 17:22 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 4 | Done
Performance Testing- ICTAK website | TMS-56 | 10062 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-09 19:52 | 2022-12-10 17:22 | 2022-12-10 20:40 | 2022-12-10 17:22 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 4 | Done
Automation of My Allocation Details & Logout pages | TMS-25 | 10031 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Vidya M Mathew | 635a8b03928dc277b905384f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-03 13:06 | 2022-12-09 19:48 | 2022-12-10 20:40 | 2022-12-09 19:48 |  | 0 | Regarding trainer allocation details | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 3 | Done
Automation of Trainer Edit profile pages | TMS-24 | 10030 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | SASILEKHA SILOSHA | 635a7df101c2ff842c18769b | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-03 13:05 | 2022-12-09 19:48 | 2022-12-10 20:40 | 2022-12-09 19:48 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 3 | Done
Automation of View Allocation and Logout pages | TMS-23 | 10029 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sneha N | 63811a65f6c85b343c093de5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-03 13:04 | 2022-12-09 19:48 | 2022-12-10 20:40 | 2022-12-09 19:48 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | TMS-37 | TMS-39 | [10 empty] | TMS Sprint 3 | Done
Automation of Admin Approval & Allocate trainer pages | TMS-22 | 10028 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sruthi Ashish | 635a943ac97f5473af707eb5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-03 13:04 | 2022-12-09 19:48 | 2022-12-10 20:40 | 2022-12-09 19:48 |  | 0 | Issues in Admin Approval and Allocate Trainer Page | Swathy Sagar | 63835f30f48fbd9b62d6820f | TMS-26 | TMS-27 | TMS-28 | TMS-29 | TMS-31 | TMS-38 | TMS-40 | TMS-41 | TMS-43 | TMS-45 | TMS-47 | TMS-49 | TMS Sprint 3 | Done
Automation of Login and Sign up pages | TMS-21 | 10027 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-12-03 13:03 | 2022-12-09 19:48 | 2022-12-10 20:40 | 2022-12-09 19:48 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 3 | Done
RTM & Defect Report ( My Allocation details, Logout) | TMS-20 | 10026 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Vidya M Mathew | 635a8b03928dc277b905384f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:23 | 2022-11-27 20:25 | 2022-12-10 20:40 | 2022-11-27 20:25 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
RTM & Defect Report ( Trainer Edit profile) | TMS-19 | 10025 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | SASILEKHA SILOSHA | 635a7df101c2ff842c18769b | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:23 | 2022-11-27 20:24 | 2022-12-10 20:40 | 2022-11-27 20:23 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
RTM & Defect Report ( View allocation, Logout ) | TMS-18 | 10024 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sruthi Ashish | 635a943ac97f5473af707eb5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:23 | 2022-11-27 20:25 | 2022-12-10 20:40 | 2022-11-27 20:25 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
RTM & Defect Report ( Allocate, Allocate trainer page) | TMS-17 | 10023 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sneha N | 63811a65f6c85b343c093de5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:22 | 2022-11-27 20:24 | 2022-12-10 20:40 | 2022-11-27 20:24 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
RTM & Defect Report ( Home, Login, Sign up, Admin approval) | TMS-16 | 10022 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:22 | 2022-11-27 20:24 | 2022-12-10 20:40 | 2022-11-27 20:24 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
Test Scenario & Test Case( My Allocation details, Logout) | TMS-15 | 10021 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Vidya M Mathew | 635a8b03928dc277b905384f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:14 | 2022-11-27 20:20 | 2022-12-10 20:40 | 2022-11-27 20:20 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
Test Scenario & Test Case( Trainer Edit profile) | TMS-14 | 10020 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | SASILEKHA SILOSHA | 635a7df101c2ff842c18769b | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:13 | 2022-11-27 20:21 | 2022-12-10 20:40 | 2022-11-27 20:21 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
Test Scenario & Test Case( View allocation , Logout) | TMS-13 | 10019 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sruthi Ashish | 635a943ac97f5473af707eb5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:13 | 2022-11-27 20:15 | 2022-12-10 20:40 | 2022-11-27 20:15 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
Test Scenario & Test Case( Allocate, Allocate Trainer page) | TMS-12 | 10018 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sneha N | 63811a65f6c85b343c093de5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:13 | 2022-11-27 20:20 | 2022-12-10 20:40 | 2022-11-27 20:20 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
Test Scenario & Test Case( Home, Login, Sign Up, Admin approval) | TMS-11 | 10017 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:12 | 2022-11-27 20:15 | 2022-12-10 20:40 | 2022-11-27 20:15 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 2 | Done
Test plan( Defect tracking, Deliverables, Templates | TMS-10 | 10016 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | SASILEKHA SILOSHA | 635a7df101c2ff842c18769b | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:01 | 2022-11-27 20:11 | 2022-12-10 20:40 | 2022-11-27 20:11 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Test plan( Assumptions, Risk, Mitigation plan) | TMS-9 | 10015 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Vidya M Mathew | 635a8b03928dc277b905384f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:01 | 2022-11-27 20:10 | 2022-12-10 20:40 | 2022-11-27 20:10 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Test plan( Test Environment, Entry & Exit Criteria, Test Automation) | TMS-8 | 10014 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sruthi Ashish | 635a943ac97f5473af707eb5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:00 | 2022-11-27 20:08 | 2022-12-10 20:40 | 2022-11-27 20:08 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Test plan( Objective, Scope, Testing Methodology) | TMS-7 | 10013 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sneha N | 63811a65f6c85b343c093de5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 20:00 | 2022-11-27 20:10 | 2022-12-10 20:40 | 2022-11-27 20:10 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Test plan( Approach, Roles & Responsibilities, Schedule) | TMS-6 | 10012 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 19:59 | 2022-11-27 20:10 | 2022-12-10 20:40 | 2022-11-27 20:10 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Requirement document( My Allocation details and Logout page) | TMS-5 | 10011 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Vidya M Mathew | 635a8b03928dc277b905384f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 19:52 | 2022-11-27 19:54 | 2022-12-10 20:40 | 2022-11-27 19:54 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Requirement document( Trainer Edit profile page) | TMS-4 | 10010 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | SASILEKHA SILOSHA | 635a7df101c2ff842c18769b | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 19:51 | 2022-11-27 19:54 | 2022-11-27 19:51 | 2022-11-27 19:54 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Requirement document( View allocation and Logout page) | TMS-3 | 10009 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sruthi Ashish | 635a943ac97f5473af707eb5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 19:50 | 2022-11-27 19:54 | 2022-12-10 20:40 | 2022-11-27 19:54 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Requirement document( Allocate and Allocate Trainer page) | TMS-2 | 10008 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Sneha N | 63811a65f6c85b343c093de5 | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 19:49 | 2022-11-27 19:54 | 2022-12-10 20:40 | 2022-11-27 19:54 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done
Requirement document(Home, Login, Sign up, Admin approval pages) | TMS-1 | 10007 | Story | Done | TMS | Trainer Management System | software | Swathy Sagar | 63835f30f48fbd9b62d6820f | Medium | Done | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | Swathy Sagar | 63835f30f48fbd9b62d6820f | 2022-11-27 19:49 | 2022-11-27 19:53 | 2022-12-10 20:40 | 2022-11-27 19:53 |  | 0 |  | Swathy Sagar | 63835f30f48fbd9b62d6820f | [12 empty] | TMS Sprint 1 | Done